{"text_format":"1","workbook":"xlsx","n_sheets":4,"sheets":["集約シート","QA分析チーム","品質分析チーム","商品開発チーム"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"集約シート","index":0,"n_rows":46,"n_cols":14,"rows_kept":46,"cut":false,"hidden":false,"merged":[[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,2,3,3],[3,4,3,5],[3,6,3,7],[3,8,4,8],[3,9,4,9],[3,10,4,10]]}
[]
[]
[]
[null,null,"大項目",null,"中項目",null,"小項目",null,"担当","開始予定","終了予定","開始実績","終了実績","進捗"]
[null,null,"項番","項目","項番","項目","項番","項目"]
[null,null,"01","QA分析","01","７月分",null,null,"虹色太郎","2021-08-01","2021-08-31","2021-08-01"]
[null,null,"01","QA分析","01","７月分",null,null,"虹色太郎","2021-09-01","2021-09-03"]
[null,null,"01","QA分析","01","７月分",null,null,"虹色太郎","2021-09-06","2021-09-09"]
[null,null,"01","QA分析","01","７月分",null,null,"虹色太郎","2021-09-10","2021-09-14"]
[null,null,"01","QA分析","01","７月分",null,null,"虹色太郎","2021-09-15","2021-09-20"]
[null,null,"01","品質分析","01","７月分",null,null,"虹色次郎","2021-08-01","2021-08-31","2021-08-01"]
[null,null,"01","品質分析","01","７月分",null,null,"虹色次郎","2021-09-01","2021-09-03"]
[null,null,"01","品質分析","01","７月分",null,null,"虹色次郎","2021-09-06","2021-09-09"]
[null,null,"01","品質分析","01","７月分",null,null,"虹色次郎","2021-09-10","2021-09-14"]
[null,null,"01","品質分析","01","７月分",null,null,"虹色次郎","2021-09-15","2021-09-20"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-08-01","2021-08-31","2021-08-01"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-09-01","2021-09-03"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-09-06","2021-09-09"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-09-10","2021-09-14"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-09-15","2021-09-16"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-09-17","2021-09-22"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-09-23","2021-09-28"]
[null,null,"01","商品開発","01","とろけるプリン",null,null,"虹色三郎","2021-09-29","2021-10-04"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[null,null,"E","E","E","E","E","E","E","E","E","E","E","E"]

{"sheet":"QA分析チーム","index":1,"n_rows":11,"n_cols":14,"rows_kept":11,"cut":false,"hidden":false,"merged":[[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,2,3,3],[3,4,3,5],[3,6,3,7],[3,8,4,8],[3,9,4,9],[3,10,4,10]]}
[]
[]
[]
[null,null,"大項目",null,"中項目",null,"小項目",null,"担当","開始予定","終了予定","開始実績","終了実績","進捗"]
[null,null,"項番","項目","項番","項目","項番","項目"]
[null,null,"01","QA分析","01","７月分","01","資料作成","虹色太郎","2021-08-01","2021-08-31","2021-08-01",null,"オンスケ"]
[null,null,"01","QA分析","01","７月分","02","チームレビュー","虹色太郎",{"$f":"WORKDAY(K6,1)","v":"2021-09-01"},{"$f":"WORKDAY(J7,2)","v":"2021-09-03"},null,null,"未着手"]
[null,null,"01","QA分析","01","７月分","03","チームレビュー指摘反映","虹色太郎",{"$f":"WORKDAY(K7,1)","v":"2021-09-06"},{"$f":"WORKDAY(J8,3)","v":"2021-09-09"},null,null,"未着手"]
[null,null,"01","QA分析","01","７月分","04","課内レビュー","虹色太郎",{"$f":"WORKDAY(K8,1)","v":"2021-09-10"},{"$f":"WORKDAY(J9,2)","v":"2021-09-14"},null,null,"未着手"]
[null,null,"01","QA分析","01","７月分","05","課内レビュー指摘反映","虹色太郎",{"$f":"WORKDAY(K9,1)","v":"2021-09-15"},{"$f":"WORKDAY(J10,3)","v":"2021-09-20"},null,null,"未着手"]
[null,null,"E","E","E","E","E","E","E","E","E","E","E","E"]

{"sheet":"品質分析チーム","index":2,"n_rows":11,"n_cols":14,"rows_kept":11,"cut":false,"hidden":false,"merged":[[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,2,3,3],[3,4,3,5],[3,6,3,7],[3,8,4,8],[3,9,4,9],[3,10,4,10]]}
[]
[]
[]
[null,null,"大項目",null,"中項目",null,"小項目",null,"担当","開始予定","終了予定","開始実績","終了実績","進捗"]
[null,null,"項番","項目","項番","項目","項番","項目"]
[null,null,"01","品質分析","01","７月分","01","資料作成","虹色次郎","2021-08-01","2021-08-31","2021-08-01",null,"オンスケ"]
[null,null,"01","品質分析","01","７月分","02","チームレビュー","虹色次郎",{"$f":"WORKDAY(K6,1)","v":"2021-09-01"},{"$f":"WORKDAY(J7,2)","v":"2021-09-03"},null,null,"未着手"]
[null,null,"01","品質分析","01","７月分","03","チームレビュー指摘反映","虹色次郎",{"$f":"WORKDAY(K7,1)","v":"2021-09-06"},{"$f":"WORKDAY(J8,3)","v":"2021-09-09"},null,null,"未着手"]
[null,null,"01","品質分析","01","７月分","04","課内レビュー","虹色次郎",{"$f":"WORKDAY(K8,1)","v":"2021-09-10"},{"$f":"WORKDAY(J9,2)","v":"2021-09-14"},null,null,"未着手"]
[null,null,"01","品質分析","01","７月分","05","課内レビュー指摘反映","虹色次郎",{"$f":"WORKDAY(K9,1)","v":"2021-09-15"},{"$f":"WORKDAY(J10,3)","v":"2021-09-20"},null,null,"未着手"]
[null,null,"E","E","E","E","E","E","E","E","E","E","E","E"]

{"sheet":"商品開発チーム","index":3,"n_rows":14,"n_cols":14,"rows_kept":14,"cut":false,"hidden":false,"merged":[[3,11,4,11],[3,12,4,12],[3,13,4,13],[3,2,3,3],[3,4,3,5],[3,6,3,7],[3,8,4,8],[3,9,4,9],[3,10,4,10]]}
[]
[]
[]
[null,null,"大項目",null,"中項目",null,"小項目",null,"担当","開始予定","終了予定","開始実績","終了実績","進捗"]
[null,null,"項番","項目","項番","項目","項番","項目"]
[null,null,"01","商品開発","01","とろけるプリン","01","商品案検討","虹色三郎","2021-08-01","2021-08-31","2021-08-01",null,"オンスケ"]
[null,null,"01","商品開発","01","とろけるプリン","02","商品案検討社内レビュー","虹色三郎",{"$f":"WORKDAY(K6,1)","v":"2021-09-01"},{"$f":"WORKDAY(J7,2)","v":"2021-09-03"},null,null,"未着手"]
[null,null,"01","商品開発","01","とろけるプリン","03","商品設計","虹色三郎","2021-09-06",{"$f":"WORKDAY(J8,3)","v":"2021-09-09"},null,null,"未着手"]
[null,null,"01","商品開発","01","とろけるプリン","04","商品開発","虹色三郎","2021-09-10",{"$f":"WORKDAY(J9,2)","v":"2021-09-14"},null,null,"未着手"]
[null,null,"01","商品開発","01","とろけるプリン","05","試食会","虹色三郎","2021-09-15",{"$f":"WORKDAY(J10,1)","v":"2021-09-16"},null,null,"未着手"]
[null,null,"01","商品開発","01","とろけるプリン","06","試食会フィードバック整備","虹色三郎","2021-09-17",{"$f":"WORKDAY(J11,3)","v":"2021-09-22"},null,null,"未着手"]
[null,null,"01","商品開発","01","とろけるプリン","07","試食会フィードバック反映","虹色三郎","2021-09-23",{"$f":"WORKDAY(J12,3)","v":"2021-09-28"},null,null,"未着手"]
[null,null,"01","商品開発","01","とろけるプリン","08","試食会（再）","虹色三郎","2021-09-29",{"$f":"WORKDAY(J13,3)","v":"2021-10-04"},null,null,"未着手"]
[null,null,"E","E","E","E","E","E","E","E","E","E","E","E"]